## Project Charter
Project Charter
Project Name | Pokémon Plushie Shop |  |  | Project Sponsor/ Business PM | Ash Ketchem
Project Start Date | 2022-08-04 | Project End Date | 2022-08-20 | Project Manager | Professor Oak
Business Needs
Recent disagreement with the country’s top one e-commerce store prohibit sellers to have a copy of a customer’s email address. On top of that, each transaction would require administrative fees which makes are plushies uncompetitive in the market. In order to secure recurring customers and be competitive in the plush space, there is a need to build an independent plushie shop.
Project Scope |  |  | Deliverables (Output and Outcome)
In Scope: Buyer interface without real payment Out of Scope: Payed web hosting and interface for an administrator |  |  | Output: A lite version of an online shop for buyers Outcome: Gradual shift from e-commerce store to standalone store
Risk and Issues Identified |  |  | Assumption and Constrains Identified
Risk: Scope creep. Expectations need be managed all throughout the project Issues: Onboarded customers may find the system in complete |  |  | Assumption: Goal is to have 400 monthly orders on the new site after 6 months Constrains: Full stack developer is a part timer
Financials
Invesment Needed (Total Cost of Ownership) |  |  | Business Financial Impact
CAPEX: 60,000 USD OPEX: N/A Total Cost of Ownership: 60,000 USD |  |  | Payback Period: 1.75 years
Milestone Schedule |  |  |  | Business Value and Impact
Project Milestones |  |  | Target Completion Date | Having an independent plush shop will enable the following benefits: Cost Reduction – the new site will enable us to save on administrative fees Recurring orders – email is still a viable tool for repeat purchases. Our company needs to secure the email addresses of our customers in order to send them promotions
Project Charter Approval |  |  | 2022-08-03
Project Kick-Off Completion |  |  | 2022-08-04
Build/Test Completion |  |  | 2022-08-20
Go-Live, Hypercare and Project Closing Completion |  |  | 2022-08-21
Benefits Tracking Completion |  |  | 2023-04-20
Project Team |  |  | Approvers / Steering Committee
IT Project Manager | Professor Oak |  | Executive Sponsor | Ash Ketchem
Technical Lead/ SME | Billy, Jessie, and Brock |  | Business PM / Lead | James and Misty
Team Members | Jed |  | Finance Business Partner | Bob