## Cover Page
Risk Register and Plan
The purpose of this document is to anticipate project risks and provide potential plans for mitigation and remediation. Risks can be quantified by using the matrix listed below
Project Name | Pokémon Plushie Shop
Project Ref No. | PRJ24
Project Manager | Professor Oak
Project Sponsor | Ash Ketchem
Name | Role | Risk Management Responsibilities
Jed | Full Stack Developer | System related
Professor Oak | Project Manager | Timeline, Budget, and Scope related
James | Commercial Business Partner | Costing of Goods related
Misty | Marketing Business Partner | Marketing related

## Risk Register and Plan
# | Risk Event | Risk Cause | Impact/Consequence | Risk Owner | Likelihood (1-5) | Consequence (1-5) | Score | Risk Rating | Mitigation and Action Plan
1 | Minor changes to scope | Miscommunications | Project will incur slight increase in spend | Ash Ketchem | 2 | 1 | 2 | Low | Ensure key stakeholders agree on the changes. Professor Oak to call meeting with Ash Ketchem in order to settle disagreement.
2 | Developer calls in sick | Covid | Timeline will increase | Jed | 2 | 4 | 8 | Med | All stakehodlers need practice proper hygiene and healthy lifestyle. In the event of illness, rebaseline is needed.
3 | Global disruption | Area lockdowns and armed conflicts | Project might get scrapped | Ash Ketchem | 3 | 5 | 15 | High | No mitigation. Rebaseline is needed