## Slide 1
Pokémon Plushie Shop
Weekly Status Report
Prepared by: Jed
Aug 13, 2022

## Slide 2
Project Background
Project Name: Pokémon Plushie Shop
Project Description: Recent disagreement with the country’s top one e-commerce store prohibit sellers to have a copy of a customer’s email address. On top of that, each transaction would require administrative fees which makes are plushies uncompetitive in the market. In order to secure recurring customers and be competitive in the plush space, there is a need to build an independent plushie shop.
Project Sponsor Group: Central Poké-team
Project Output: Stand alone ordering plushie shop
Project Outcome: Drive 400 monthly buyers to order at the new site
Vendor partner: Jed

## Slide 3
Active Project Schedule
Project Activity | Planned date | Actual date acheived
Kick-off | Aug 4, 2022 | Aug 4, 2022
View all plushies | Aug 5, 2022 | Aug 5, 2022
Select a plushie | Aug 8, 2022 | Aug 8, 2022
Add to cart | Aug 9, 2022 | Aug 9, 2022
Fill-up order form | Aug 15, 2022 | * we are here!
Subscribe to newsletter | Aug 18, 2022 | 
Search bar | Aug 20, 2022 | 
Mock a subscrition email notif | Aug 20, 2022 | 
Final GitHub push | Aug 20, 2022 | 
Fulfil closing documents | Aug 22, 2022 | 

## Slide 4
Update Summary
STATUS | COST | TIME | SCOPE
Previous | ⬤ | ⬤ | ⬤
Current | ⬤ | ⬤ | ⬤
RAG Status Details
Cost and scope are within baseline. Time is at risk of missing baseline due to peak-workload of the developer’s full-time work.
ACHIEVEMENTS
Kick-off was done. Majority of the functionalities are completed which include viewing all plushies, showing a single plushie, and checkout page.
NEXT STEPS AND HELP NEEDED
Next is to develop the mock pay-out process, subscribing to a newsletter, and other low impact features.

## Slide 5
Risk logs
No. | Risk Desc. | Date opened | Current status | Owner | Risk response
1 | Missed timeline due to work load | Aug 13, 2022 | Closed | Jed | Blocked time throughout the next week in order to fulfill tasks

## Slide 6
Issue logs
No. | Issue Desc. | Date opened | Current status | Owner | Issue response

## Slide 7
Thank you!