## Slide 1
Pokémon Plushie Shop
Weekly Status Report
Prepared by: Jed
Aug 22, 2022

## Slide 2
Project Background
Project Name: Pokémon Plushie Shop
Project Description: Recent disagreement with the country’s top one e-commerce store prohibit sellers to have a copy of a customer’s email address. On top of that, each transaction would require administrative fees which makes are plushies uncompetitive in the market. In order to secure recurring customers and be competitive in the plush space, there is a need to build an independent plushie shop.
Project Sponsor Group: Central Poké-team
Project Output: Stand alone ordering plushie shop
Project Outcome: Drive 400 monthly buyers to order at the new site
Vendor partner: Jed

## Slide 3
Active Project Schedule
Project Activity | Planned date | Actual date acheived
Kick-off | Aug 4, 2022 | Aug 4, 2022
View all plushies | Aug 5, 2022 | Aug 5, 2022
Select a plushie | Aug 8, 2022 | Aug 8, 2022
Add to cart | Aug 9, 2022 | Aug 9, 2022
Fill-up order form + Search bar | Aug 15, 2022 | Aug 18, 2022
Subscribe to newsletter | Aug 18, 2022 | Aug 15, 2022
Mock a subscrition email notif | Aug 20, 2022 | Aug 16, 2022
Complete migration (*new) | Aug 26, 2022 | *we are here!
Go-Live | Aug 20, 2022 | 
Fulfil closing documents | Aug 22, 2022 | 

## Slide 4
Update Summary
STATUS | COST | TIME | SCOPE
Previous | ⬤ | ⬤ | ⬤
Current | ⬤ | ⬤ | ⬤
RAG Status Details
Cost and scope are within baseline. Original planned timeline is extended by a full week due to deployment issues and peak-workload of the developer’s full-time work.
ACHIEVEMENTS
New functionalities were added which includes fill-up order form, search feature, newsletter subscription, and mock email notifications.
NEXT STEPS AND HELP NEEDED
Next is to complete migration of old repository to new repository. Then, all functionalities need to be working as intended. Finally, go-live to Heroku website can happen.

## Slide 5
Risk logs
No. | Risk Desc. | Date opened | Current status | Owner | Risk response
1 | Missed timeline due to work load | Aug 13, 2022 | Closed | Jed | Blocked time throughout the next week in order to fulfill tasks

## Slide 6
Issue logs
No. | Issue Desc. | Date opened | Current status | Owner | Issue response
1 | Missed timeline due to deployment challenges | Aug 20, 2022 | Closed | Jed | Extended timeline was granted but to keep planned timeline for documentation

## Slide 7
Thank you!